{"text_format":"3","workbook":"xls","n_sheets":7,"sheets":["2-1 城镇生活污水","2-2工业集聚区","2-3河道整治","2-4重点行业、企业污染治理","2-5农村环境综合","2-6水源地规范化建设","附表2-8其他类项目"],"not_rendered":{"external_links":1,"defined_names":18},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"2-1 城镇生活污水","index":0,"n_rows":68,"n_cols":11,"rows_kept":68,"merged":[[0,0,0,8],[1,0,2,0],[1,1,2,1],[1,2,1,3],[1,4,2,4],[1,5,2,5],[1,6,2,6],[1,7,2,7],[1,8,2,8],[30,8,31,8],[44,8,46,8]],"flags":["formulas_cached_only"]}
["附件2：                    \n                            内蒙古2017年度水污染防治重点工程项目表\n\n                                  表1   城镇生活污水处理设施建设项目表"]
["序号","项目名称","建设地点",null,"目标水体","建设周期","责任单位","建设内容及规模","项目总投资（万元）"]
[null,null,"地级行政区","县级行政区"]
[1,"和林县城关镇管网改造工程","呼和浩特市","和林县","大黑河","2017年-2018年","和林县住建局","新建污水收集管网 总长8.459公里",2470]
[2,"污水处理厂污泥处理处置工程","呼和浩特市","赛罕区","大黑河","2017年-2018年","呼和浩特春华水务开发集团有限责任公司","章盖营污水处理厂新建300吨/日污泥处置系统",3000]
[3,"新城区棚户区改造","呼和浩特市","新城区","大黑河","2017年","新城区住建局","新建污水收集管网 总长5公里",800]
[4,"新城区市政基础设施改造","呼和浩特市","新城区","大黑河","2017年","新城区住建局","新建污水收集管网  6公里",10000]
[5,"武川县金三角开发区东西污水管网连接工程","呼和浩特市","武川县","大黑河","2017年","武川县金三角开发区","新建污水收集管网  9公里",3980]
[6,"武川县可镇城镇雨污分流管网建设工程","呼和浩特市","武川县","大黑河","2017年","武川县住建局","新建雨污分流管网  5.5公里",2500]
[7,"武川县可镇污水处理厂好氧池保温建设工程","呼和浩特市","武川县","大黑河","2017年","武川县水务局","可镇污水处理厂好氧池保温建设工程",200]
[8,"公主府污水处理厂深度处理工程","呼和浩特市","回民区","大黑河","2016年-2018年","呼和浩特春华水务开发集团有限责任公司","设计规模为5万吨/日",14197]
[9,"土默特左旗察素齐镇污水处理厂提标改造工程","呼和浩特市","土默特左旗","大黑河","2017年","土默特左旗城发公司","升级改造察素齐镇2万吨/日污水处理厂，污染物排放标准由设计的一级B提升级到一级A；建设中水输配水管线4.3公里",2893,null,1]
[10,"九原区阿嘎如泰苏木中心集镇污水处理厂建设项目","包头市","九原区","昆都仑河","2016年-2017年","九原区政府","建设处理规模为3000吨/日污水处理设施及配套管网。",6000]
[11,"万水泉污水处理厂二期扩建工程","包头市","高新区","二道沙河","2014年-2018年","包头市排水产业有限责任公司","新建7.5万吨/日污水处理厂及配套工程，建成后总规模15万吨/日",24000]
[12,"二道沙河沿包伊公路至万水泉污水处理厂污水收集管网建设工程","包头市","高新区","二道沙河","2017年","市城建委","建设污水收集管网4.5公里",4843]
[13,"西河污水收集总干管建设工程","包头市","东河区\n高新区","二道沙河","2016年-2017年","包头市排水产业有限责任公司","新建污水收集管网 7.4公里",6000]
[14,"包头市西南区域污水资源化利用工程","包头市","高新区\n九原区","昆都仑河","2016年-2017年","包头市排水产业有限责任公司","新建污水收集管网 11.4公里，再生水管线4.5公里，10万吨/日污水提升泵站",3000]
[15,"扎赉诺尔污水处理厂提标改造及中水回用管线工程","呼伦贝尔市","扎赉诺尔区","达兰鄂罗木河、海拉尔河、呼伦湖、新开河","2016年-2018年","扎赉诺尔区政府","增加超滤膜处理工艺，出水水质达到中水回用标准，铺设中水管线43.6公里",9000,null,1]
[16,"兴安盟科右中旗巴彦呼舒镇污水处理厂扩建及配套管网工程","兴安盟","科右中旗","霍林河","2016年—2017年","科右中旗南鼎乌苏污水处理中心","日处理能力2万吨，新建净化间、接触池、加氯加药间和中水供水管线6.5公里",3500]
[17,"乌兰浩特市利环污水处理厂污泥处理工程","兴安盟","乌兰浩特市","洮儿河","2017年-2018年","利环污水处理厂","日处理污泥70吨，用地面积17020平方米。建设发酵车间、加工成品车间、辅料车间、生物滤池等构筑物",4265]
[18,"科左中旗舍伯吐镇污水处理工程(一期)建设项目","通辽市","科左中旗","西辽河","2017年-2018年","科左中旗住建局","处理规模0.60万吨/日",4578.79]
[19,"通辽市城东污水\n处理厂工程","通辽市","科尔沁区","西辽河","2017年","通辽市城东污水处理厂","污水提升泵房、格栅池、旋流沉砂池、AA/O生化池、二沉池、混合反应沉淀池、加药过滤消毒间、污泥处理系统、污水管网收集系统及附属设施等",10303.78]
[20,"科左后旗甘旗卡镇东区污水处理厂","通辽市","科左后旗甘旗卡镇","西辽河","2016年-2017年","住建局","新建处理能力为2万吨/日的污水处理厂一座，提升泵站2座，污水管网18.47公里，中水管网4公里","14061.32\n\n"]
[21,"赤峰市巴林左旗再生水利用设施建设项目","赤峰市","巴林左旗","乌尔吉沐沦河","2015年-2017年","巴林左旗清源污水处理厂","项目建成后再生水供水能力达到1.7万吨/日",6607.61]
[22,"巴林左旗清源污水处理厂中水扩建工程","赤峰市","巴林左旗","乌尔吉沐沦河","2017年-2019年","巴林左旗清源污水处理厂","新建3万吨/日中水厂1座",3600]
[23,"克什克腾旗污水处理厂污泥处置工程","赤峰市","克什克腾旗","西辽河","2017年-2018年","克什克腾旗污水处理厂","日处理干泥20吨污泥处置设施",400]
[24,"克什克腾旗污水处理厂管网扩建工程","赤峰市","克什克腾旗","西辽河","2016年-2020年","克什克腾旗污水处理厂","新建污水收集管网 12公里",450]
[25,"宁城县城区污水管网工程","赤峰市","宁城县","老哈河","2016年—2017年","宁城县污水处理工程建设管理处","污水管网11.8公里、污水提升泵站一座",2393.02]
[26,"赤峰市宁城县八里罕镇镇区污水处理工程","赤峰市","宁城县","老哈河","2015年-2017年","宁城县污水处理工程建设管理处","新建0.5万吨/日污水处理厂1座及污水管网26公里",4300]
[27,"翁牛特旗再生水利用及污泥处置工程","赤峰市","翁牛特旗","少郎河","2016年-2017年","翁牛特旗乌丹污水处理厂","建设规模为处理再生水2万吨/日，处理污泥30吨/日；中水管网20.74公里及相应的附属工程",5230]
[28,"喀喇沁旗锦山污水处理厂建设工程","赤峰市","喀喇沁旗","老哈河","2015年-2017年","喀喇沁旗住房和城乡建设局","新建2万吨/日污水处理厂1座",8330.46]
[29,"喀喇沁旗锦山镇污泥处理工程","赤峰市","喀喇沁旗","锡伯河","2017年-2018年","喀喇沁旗住房和城乡建设局","新建20吨/日湿污泥处置间"]
[30,"喀喇沁旗锦山污水处理厂中水回用工程","赤峰市","喀喇沁旗","老哈河","2015年-2017年","喀喇沁旗住房和城乡建设局","新建2万吨/日中水回用工程",5429.21]
[31,"喀喇沁旗乃林镇污水处理厂工程","赤峰市","喀喇沁旗","老哈河","2016年-2017年","喀喇沁旗住房和城乡建设局","新建0.5万吨/日污水处理工程",4571]
[32,"元宝山区污水处理厂中水综合利用供水项目","赤峰市","元宝山区","老哈河","2017年-2020年","元宝山区水利局","中水厂一座6万吨/日，供水管道51.6公里",42695.35]
[33,"敖汉旗新惠城区污水处理厂二期工程","赤峰市","敖汉旗","孟克河","2017年-2018年年","敖汉旗新惠城区污水处理厂","日处理3万吨污水处理厂一座",7086.55]
[34,"赤峰市红庙子污水处理二期扩建工程","赤峰市","红山区","英金河","2016年-2020年","赤峰市德润排水有限责任公司","新建规模2.5万吨/日污水处理厂一座，以及相应附属设施。",13187]
[35,"赤峰市中心城区再生水利用配套管网一期工程","赤峰市","红山区经济开发区","老哈河","2015年-2018年","赤峰市德润排水有限责任公司","新建管径Dn500—Dn1000mm再生水管网37.95公里及相应附属工程，建成后供水能力为10万吨/日。",15189]
[36,"赤峰市中心城区再生水利用配套管网三期工程","赤峰市","红山区经济开发区","老哈河","2016年-2017年","赤峰市德润排水有限责任公司","新建再生水输水干管2*12.9公里以及相应的附属设施。建设规模为输水能力9万吨/日。",16492]
[37,"丰镇市城市中水回用工程项目","乌兰察布市","丰镇市氟化工业园区","御河堡子湾","2015年-2017年","丰镇市洁源中水回用厂","新建2万吨/日中水处理厂；建设内容有土建、设备购置安装及相应附属配套设施，铺设管道3公里",4836]
[38,"内蒙古华伊卓资热电有限公司回用卓资县污水处理厂中水增量建设项目","乌兰察布市","卓资县卓资山镇污水处理厂厂址内西侧","大黑河","2016年-2017年","内蒙古华伊卓资热电有限公司","铺设管道28.406公里,使用卓资县污水处理厂再生水。",9988.45]
[39,"乌兰察布市卓资县旗下营镇污水处理工程","乌兰察布市","卓资县旗下营工业区西区斗金山小西沟","大黑河","2013年-2016年","卓资县住房和城乡建设局","处理污水1万吨/日，采用曝气生物滤池处理工艺，配套建设污水管网及污水处理设施",5506.91]
[40,"乌兰察布市察右中旗科布尔镇污水处理厂再生水利用建设项目","乌兰察布市","察右中旗科布尔镇污水处理厂内","大黑河","2016年-2018年","察右中旗环境保护局","处理污水1万吨/日，采用A2/O工艺，配套建设污水管网及污水处理设施",3708.82]
[41,"乌兰察布市四子王旗乌兰花镇污水处理厂中水回用工程","乌兰察布市","四子王旗乌兰花镇污水处理厂","锡林河","2013年-2017年","四子王旗城市建设投资开发有限责任公司","新建中水回收处理厂1座，处理中水0.75万吨/日，建设中水管道25.6公里。",4071.47]
[42,"南郊污水厂中水回用工程","鄂尔多斯市","东胜区","乌兰木伦河","2017年","东胜区人民政府","增加中水回用11000吨/日",93800]
[43,"万利污水厂中水回用工程","鄂尔多斯市","东胜区","乌兰木伦河","2017年","东胜区人民政府","增加中水回用5000吨/日"]
[44,"北郊污水厂中水回用工程","鄂尔多斯市","东胜区","乌兰木伦河","2017年","东胜区人民政府","增加中水回用60000吨/日"]
[45,"康巴什赛车城北侧绿地景观水体配套建设项目","鄂尔多斯市","康巴什","乌兰木伦河","2017年","康巴什新区管理委员会","建设景观水体132601平方米",5000]
[46,"康巴什新区中水管道维修项目","鄂尔多斯市","康巴什","乌兰木伦河","2017年","康巴什新区管理委员会","中水回用管线维护，11公里",744.4172]
[47,"鄂尔多斯市康巴什新区污水处理厂提标改造工程","鄂尔多斯市","康巴什新区","乌兰木伦河","2017年-2018年","康巴什新区管理委员会","提标改造总规模：3万 吨/日，分期实施，其中，一期规模 1.5 万 吨/日，二期规模 1.5 万吨/日。（核实建设周期）",5698.24]
[48,"纳日松镇污水处理厂","鄂尔多斯市","准格尔旗","㹀牛川","2016年-2017年","准格尔旗人民政府","建设1100吨/日（一期500吨/日）污水处理厂1座",844]
[49,"准格尔召镇污水处理厂","鄂尔多斯市","准格尔旗","㹀牛川","2016年-2017年","准格尔旗人民政府","建设3000吨/日（一期建设750吨/日）污水处理厂1座",3357.59]
[50,"达拉特旗污泥处理处置厂","鄂尔多斯市","达拉特旗","黄河","2017年","达拉特旗人民政府","污泥处置20吨/日",2175]
[51,"鄂尔多斯市乌审旗嘎鲁图镇污水处理厂提标改造及再生水回用工程","鄂尔多斯市","乌审旗","海流图河","2017年-2018年","乌审旗人民政府","将1.5万吨/日污水处理厂提标改造至一级A；新建1.2万吨/日中水处理厂1座，中水管网62.5公里，及相应的附属工程。",9672]
[52,"乌审旗污水管网改造工程","鄂尔多斯市","乌审旗","海流图河","2017年-2018年","乌审旗人民政府","新建污水管网25公里",3750]
[53,"鄂托克前旗敖镇污水处理提标改造工程","鄂尔多斯市","鄂托克前旗","黄河","2017年-2018年","鄂托克前旗人民政府","将0.75万吨/日污水处理厂提标改造至一级A",13300]
[54,"敖镇西北及南部片区污水管网改造","鄂尔多斯市","鄂托克前旗","都斯兔河","2017年","鄂托克前旗人民政府","铺设污水管网2.6公里",260]
[55,"五原县城镇污水处理厂扩容改造项目","巴彦淖尔市","五原县","总排干/乌梁素海","2016年-2017年","五原县城镇污水处理厂","1.改进现有2.2万吨/日污水处理厂工艺，使污水稳定达标排放\n2.新建一座2.2万吨/日污水处理厂，建设管网41.708公里",14593.11]
[56,"巴彦淖尔市乌拉特后旗巴音宝力格镇污水处理厂扩建工程","巴彦淖尔市","乌拉特后旗","总排干/乌梁素海","2016年-2017年","乌拉特后旗富泉水务有限责任公司","规模由原来的日处理0.6万吨扩建到日处理1.2万吨",4245.75]
[57,"巴彦淖尔市临河东城区污水处理厂提标改造工程","巴彦淖尔市","临河区","总排干/乌梁素海","2017年","经济技术开发区管委会","建成10万吨/日污水处理从一级B到一级A提标改造系统一套",5500]
[58,"巴彦淖尔市临河东城区污水管网扩建工程","巴彦淖尔市","临河区","总排干/乌梁素海","2015年-2017年","经济技术开发区管委会","扩建污水管网23.68公里,新建污水提升泵站2座，污水箱涵6.4公里",9850]
[59,"杭锦后旗亿源水务有限公司污水处理厂改扩建项目","巴彦淖尔市","杭锦后旗","总排干/乌梁素海","2017年","杭锦后旗亿源水务有限公司污水处理厂","对2万吨/日现有污水处理设施提标改造至一级A标准。",1326.51]
[60,"阿拉善盟巴彦浩特新区污水处理工程","阿拉善","阿左旗","黄河","2015年-2017年","阿拉善左旗城市给排水公司","厂区平整绿化、设备调试运行、厂外管网剩余部分的安装",9899]
[61,"阿拉善盟吉兰泰镇污水处理工程","阿拉善","阿左旗","黄河","2017年","吉兰泰镇人民政府","厂区污水泵站、细格栅及沉砂池、膜格栅、调节池及生物反应池、MBR池设备间及接触消毒池、匀质池、脱水机房及泥棚、清水池、回用水泵房、综合办公楼、深井取水泵房等及其配套附属设施，新建污水管网9.2Km、中水管网1.9公里",5100.8]
[62,"达来呼布镇再生水利用及污泥处置项目","阿拉善","额济纳旗","额济纳河","2017年","额旗住建局","1、新建污水再生利用厂，新建中水管网11.2公里及配套附属设施；2、新建日处理5吨污泥处理厂；3、污水检测化验设备",6000]
[63,"策克口岸污水处理工程","阿拉善","额济纳旗","额济纳河","2017年","口岸规划建设局","新建污水处理500吨/日，2个提升泵站，排污主管网30公里",3000]
[64,"乌达区老旧供水管网改造工程","乌海市","乌达区","黄河","2017年-2021年","住建委","改造给水管网，22.67公里",2238.73]
[65,"海勃湾地下综合管廊工程","乌海市","海勃湾区","黄河","2017年","住建委","新建建设路综合管廊，6公里",70000]

{"sheet":"2-2工业集聚区","index":1,"n_rows":33,"n_cols":9,"rows_kept":33,"merged":[[0,0,0,8],[1,0,2,0],[1,1,2,1],[1,2,2,2],[1,3,1,4],[1,5,2,5],[1,6,2,6],[1,7,2,7],[1,8,2,8]],"flags":["formulas_cached_only"]}
["表2 工业集聚区污水集中处理与在线监测设施项目表"]
["序号","项目名称","所在工业集聚区名称","建设地点",null,"责任单位","建设周期","建设内容及规模","项目总投资\n（万元）"]
[{"$nulls":3},"地级行政区","县级行政区"]
[1,"包头市土右旗新型工业园区污水处理（一期）工程建设项目","包头市土右旗新型工业园区","包头市","土右旗","土右旗政府","2015年-2017年","新建3万吨/日污水处理厂",32197]
[2,"固阳县金山工业园区污水资源化利用工程","包头市固阳县金山工业园区","包头市","固阳县","固阳县政府","2016年-2017年","新建2万吨/日污水处理厂",4864]
[3,"满洲里市扎赉诺尔重化工业基地污水处理厂工程","扎赉诺尔重化工业基地","呼伦贝尔市","扎赉诺尔区","扎赉诺尔区政府","2014年-2017年","处理规模0.5万吨/日，新建管网15公里。主要处理园区东西区及满西基地的生产废水和生活污水。",7205]
[4,"木里图污水处理厂湿地改造工程","科尔沁区工业园区","通辽市","科尔沁区","木里图污水处理厂","2017年","（1）人工湿地工程处理规模为50000吨/日\n（2）中水回用工程的设计进水处理量：35000吨/日",14000]
[5,"霍林郭勒市沙尔呼热独立工矿区新建中水管网工程","霍林郭勒工业园区","通辽市","霍林郭勒市"," 霍林郭勒市住房和城乡建设局 ","2017年-2018年","建设DN600焊接管中水管线20公里，配套建设3座提升泵站，各泵站安装配套设备2套，管线沿途建设阀门井20座。",8000]
[6,"内蒙古林西工业园区污水处理工程","内蒙古林西工业园区","赤峰市","林西县","林西县金鼎工业园区管理委员会","2017年-2019年","新建1万吨/日污水处理厂",6989.21]
[7,"乌达经济开发区污水处理厂扩建及中水回用项目","乌达经济开发区","乌海市","乌达区","环保局","2017年","1、污水处理厂扩建设施安装调式并投入运行，3.2万吨/日\n2、新建2.6万吨/日中水回用工程",14550]
[8,"海南工业园区污水处理厂二期","海南经济开发区","乌海市","海南区","环保局","2017年","完成二期工程建设，安装调式并投入运行，3万吨/日",16800]
[9,"内蒙古源宏精细化工有限公司","乌达经济开发区","乌海市","乌达区","环保局","2017年","铺设进入污水处理厂管道，企业出口安装在线监测设施、与环保部门联网并通过验收",12]
[10,"内蒙古佳瑞米精细化工有限公司","乌达经济开发区","乌海市","乌达区","环保局","2017年","铺设进入污水处理厂管道，企业出口安装在线监测设施、与环保部门联网并通过验收",12]
[11,"内蒙古腾龙生物精细化工有限公司","乌达经济开发区","乌海市","乌达区","环保局","2017年","铺设进入污水处理厂管道，企业出口安装在线监测设施、与环保部门联网并通过验收",12]
[12,"内蒙古华电乌达热电有限公司","乌达经济开发区","乌海市","乌达区","环保局","2017年","铺设进入污水处理厂管道，企业出口安装在线监测设施、与环保部门联网并通过验收",12]
[13,"内蒙古君正能源有限公司（化工、电厂）","乌达经济开发区","乌海市","乌达区","环保局","2017年","铺设进入污水处理厂管道，企业出口安装在线监测设施、与环保部门联网并通过验收",12]
[14,"内蒙古宜化化工有限公司（化工、电厂）","乌达经济开发区","乌海市","乌达区","环保局","2017年","铺设进入污水处理厂管道，企业出口安装在线监测设施、与环保部门联网并通过验收",12]
[15,"乌海市良峰精细化工有限公司","乌达经济开发区","乌海市","乌达区","环保局","2017年","铺设进入污水处理厂管道，企业出口安装在线监测设施、与环保部门联网并通过验收",5]
[16,"内蒙古东源科技有限公司（电厂、化工）","乌达经济开发区","乌海市","乌达区","环保局","2017年","铺设进入污水处理厂管道，企业出口安装在线监测设施、与环保部门联网并通过验收",12]
[17,"内蒙古恒业成有限公司（电厂、化工）","乌达经济开发区","乌海市","乌达区","环保局","2017年","铺设进入污水处理厂管道，企业出口安装在线监测设施、与环保部门联网并通过验收",5]
[18,"乌海市黑猫三兴有限公司","海南经济开发区","乌海市","海南区","环保局","2017年","新建废水预处理设施，企业出口安装在线监测设施、与环保部门联网并通过验收",4000]
[19,"内蒙古宝宏化工有限公司","海南经济开发区","乌海市","海南区","环保局","2017年","新建废水预处理设施，企业出口安装在线监测设施、与环保部门联网并通过验收",500]
[20,"海南区西来峰工业园再生水及资源综合利用项目","海南经济开发区","乌海市","海南区","环保局","2017年","新建中水回用工程，安装调式并投入运行5000吨/日",2100]
[21,"乌海市海南区新建污水管网工程","海南经济开发区","乌海市","海南区","住建委","2017年","新建污水管网，8公里",870]
[22,"阿拉善经济开发区污水处理有限责任公司污水处理设施改造项目","阿拉善经济开发区","阿拉善盟","阿拉善经济开发区","阿拉善经济开发区污水处理有限责任公司","2017年","对生化处理系统升级改造，增加甲醇、活性炭等投加单元，维持二沉出水稳定达标；对深度处理系统进行升级改造，增加转盘过滤器、多介质过滤器、更换超滤膜、反渗透膜，增加浓盐水反渗透处理系统，保证再生水回用率维持在80%以上，降低浓盐水排放量；完善再生水管网，保证再生水供应于所有用水大户。",5000]
[23,"腾格里经济技术开发区中环万代水质净化厂项目","腾格里经济技术开发区","阿拉善盟","腾格里经济技术开发区","阿拉善盟中环万代环境产业有限公司","2017年","处理工业废水原水量2000吨/日配套相关设备。",33291.9]
[24,"丰镇市重化工业园区污水处理改扩建工程","丰镇市重化工业园区","乌兰察布市","丰镇市","丰镇市重化工业园区","2016年-2017年","1、东园区已建污水厂升级改造工程：0.5万吨/日；\n2、东园区污水厂扩建工程：0.3万吨/日；\n3、西园区已建污水厂升级改造工程：1.5万吨/日；\n4、西园区污水厂扩建工程：0.5万吨/日",9719.61]
[25,"海南工业园综合管廊（一期）","海南经济开发区","乌海市","海南区","乌海经济开发区海南工业园管理委员会","2017年","新建2.7公里综合管廊",3880]
[26,"上海庙污水处理厂提标改造","鄂尔多斯市","鄂托克前旗","黄河流域","上海庙经济开发区管委会","2017年","新增厌氧缺氧池、高效澄清池及纤维滤池、混合液及污泥回流系统",1500]
[27,"圣圆煤化工基地污水处理厂建设项目","鄂尔多斯市","伊金霍洛旗","㹀牛川","伊金霍洛镇人民政府","2016年-2017年","建设1000吨/日污水处理厂1座",5800]
[28,"库伦沈阳工业园区污水处理厂","通辽市","库伦旗","西辽河","库伦旗国有资产投资经营有限公司","2014年-2017年","设计规模为处理污水1.0×104m3/d，建设格栅渠、格栅池、好氧池、二沉池、污泥浓缩池、污水事故池、在线监控机房和办公区等",5696.35]
[29,"库伦旗三家子污水处理厂","通辽市","库伦旗","西辽河","库伦旗国有资产投资经营有限公司","2016年-2017年","设计规模为处理污水1.0×104m3/d，建设格栅间、沉砂池、均质调节池、水解池、二沉池、AO生化池、中间水池、BAF池、清水消毒池及回用泵、应急事故池和污泥处理系统",4319.89]
[30,"内蒙古通辽市奈曼旗化工园区地下水修复一期工程（南区）\n","通辽市","奈曼旗","西辽河","哈尔滨辰能工大环保科技股份有限公司","2017年-2018年","建设取水及回注系统、给水站系统及臭氧机房、鼓风机房、配电室、办公室等辅助设施",1563.86]

{"sheet":"2-3河道整治","index":2,"n_rows":22,"n_cols":9,"rows_kept":22,"merged":[[0,0,0,8],[1,0,2,0],[1,1,2,1],[1,2,1,3],[1,4,2,4],[1,5,2,5],[1,6,2,6],[1,7,2,7],[1,8,2,8]],"flags":["formulas_cached_only"]}
["表3    河道整治项目表"]
["序号","项目名称","建设地点",null,"目标水体","建设周期","责任单位","建设内容及规模","项目总投资（万元）"]
[null,null,"地级行政区","县级行政区"]
[1,"新城区古路板河道治理","呼和浩特市","新城区","大黑河","2017年","新城区农牧业水利局","治理河道3.8公里",2507]
[2,"玉泉区小黑河河道综合治理项目","呼和浩特市","玉泉区","小黑河（云中路-乌素图河下游段）","2017年-2019年","玉泉区土地储备项目服务中心","治理长度6.2公里，项目区段范围内征拆工作",298000]
[3,"扎达盖河综合治理工程","呼和浩特市","玉泉区","扎达盖河（鄂尔多斯大街~小黑河段）","2016年-2018年","玉泉区土地储备项目服务中心","综合治理长度4.860公里新建气盾坝4座。",67697.03]
[4,"乌素图河综合治理工程","呼和浩特市","回民区、玉泉区","大黑河","2017-2018","呼和浩特春华水务开发集团有限责任公司","河道综合治理起点乌素图水库，终点至小黑河，长度为14.8公里",521137.8]
[5,"呼和浩特市哈拉更干沟（京包铁路-秀水街）综合治理工程","呼和浩特市","赛罕区","大黑河","2016年-2018年","呼和浩特春华水务开发集团有限责任公司","河道治理长度 3.16公里",158105.05]
[6,"大黑河城区段综合整治工程","呼和浩特市","玉泉区、赛罕区","大黑河","2017年-2019年","呼和浩特市水务局","治理河段长度 14公里",31800]
[7,"昆都仑河下游环境整合治理项目","包头市","昆区","昆都仑河","2017年","昆区政府","治理河段 4.5公里",18000]
[8,"东河区河湖连通工程","包头市","东河区","东河","2016年-2018年","东河区政府","治理河段长度4.6公里",10000]
[9,"西河河道整治工程","包头市","东河区","西河","2016年-2017年","东河区政府","治理河段长度5.66公里",10000]
[10,"东河区头道沙河（西井湾）景观河道综合治理工程","包头市","东河区","西河","2016年-2017年","东河区政府","治理河段长度 3.8公里",1500]
[11,"东河区西水道—西河景观河道综合治理工程","包头市","东河区","西河","2016年-2017年","东河区政府","治理河段长度 1.3公里",1000]
[12,"九原区四道沙河河道疏浚及景观建设工程","包头市","九原区","四道沙河","2016年-2017年","九原区政府","治理河段长度 1.4公里",1300]
[13,"九原区二道沙河景观建设改造工程","包头市","九原区","二道沙河","2015年-2017年","九原区政府","治理河段长度 4.69公里",5670]
[14,"西露天排污渠治理工程","赤峰市","元宝山区","老哈河",2017,"元宝山区住房和城乡建设局","黑臭水体面积4723平方米，黑臭水体长度1.071公里，设计管线长2.059公里，截污纳管、生物残体及漂浮物淤泥垃圾清理、清淤疏浚、岸带修复，旁路治理",563.4494]
[15,"西旱河清淤\n工程","赤峰市","元宝山区","老哈河",2017,"元宝山区住房和城乡建设局","黑臭水体面积4322.5平方米，黑臭水体长度1.235公里，淤泥垃圾清理，路基清表、挖运弃土方、挖除树根",53.0892]
[16,"中心城区防洪及环城水系治理工程","赤峰市","红山区\n松山区\n喀喇沁旗","锡泊河、\n半支箭河、阴河、\n英金河、\n海苏沟、\n小西沟","2017-2019年","赤峰市水利局","防洪工程、生态景观工程、水系补源工程、水质保护工程及改建段生态修复工程，主要涉及锡泊河、英金河、阴河、小西沟、海苏沟、半支箭河等6条河道的治理，治理长度40.8公里（其中，新治理河道长度约33.0公里，改建河道长度约7.8公里），防洪标准百年一遇。",316037.91]
[17,"滦河流域多伦县段水环境综合整治项目","锡林郭勒盟","多伦县","滦河","2015-2017","多伦县人民政府","龙泽湖公园上游湿地生态修复工程、污水处理厂出水口湿地生态修复工程、滦河沿岸河道清浚及边坡护理工程、分散式畜禽养殖污染治理工程",32700]
[18,"丰镇市黑河河道（城区段）污染防治综合治理工程","乌兰察布市","丰镇市城区","御河堡子湾","2016年-2018年","丰镇市环境保护局","河底清淤160.88万立方米;河坡整治面积1910平方米",17159]
[19,"兴和县二道河（海河）河道治理工程","乌兰察布市","兴和县城关镇前、后河","御河堡子湾","2016年-2018年","兴和县水利局","新建防洪河段全长12.99公里",6655.36]

{"sheet":"2-4重点行业、企业污染治理","index":3,"n_rows":31,"n_cols":10,"rows_kept":31,"merged":[[0,0,0,8],[1,0,2,0],[1,1,2,1],[1,2,1,3],[1,4,2,4],[1,5,2,5],[1,6,2,6],[1,7,2,7],[1,8,2,8]],"flags":["formulas_cached_only"]}
["表4 重点行业、企业污染治理项目表",{"$nulls":8}," "]
["序号","项目名称","建设地点",null,"目标水体","建设周期","责任单位","建设内容及规模","项目总投资（万元）"]
[null,null,"地级行政区","县级行政区"]
[1,"华美公司西厂硫酸镁循环利用项目","包头市","昆区","昆都仑河","2016年-2017年","华美稀土有限公司","对90万吨/年华美西厂硫酸镁废水资源化处置，循环利用",12650]
[2,"华美公司西厂氢氟酸再生项目","包头市","昆区","昆都仑河","2016年-2017年","华美稀土有限公司","28120吨/年，对氢氟酸进行高效回收后资源化利用，生产高品质的氟盐和氟化稀土",3800]
[3,"包头市玺骏稀土有限责任公司稀土湿法冶金废水处理工艺及设备升级改造项目","包头市","昆区","昆都仑河","2016年-2017年","包头市玺骏稀土有限责任公司","建成MVR技术结晶蒸发200吨/日能力稀土湿法冶金废水处理线，冷凝水全部返回生产线",1600]
[4,"华电内蒙古能源有限公司包头发电分公司节水零排放\n工程","包头市","九原区","昆都仑河","2016年-2017年","华电内蒙古能源有限公司包头发电分公司","在完善全厂废水梯级利用节水技改工作后，按照120吨/小时的处理量进行设计改造，产水全部回用",4200]
[5,"奈曼旗鑫凯食品有限责任公司畜禽屠宰场污水处理项目","通辽市","奈曼旗","西辽河","2017年","奈曼旗鑫凯食品有限责任公司","本项目总占地面积为100平方米，建设处理能力为200吨/日的屠宰场污水处理站以及相配套的污水处理设备，采购及配套理化分析检验、化验分析设备及其他相关配套设施",106.115]
[6,"牧原食品股份有限公司奈曼三区一场生猪养殖项目","通辽市","奈曼旗","西辽河","2017年","内蒙古奈曼牧原农牧有限公司","主要建设猪舍、粪污处理设施、沼液农灌设施、有机肥制造工程及供电、供热等辅助工程",34098.97]
[7,"牧原食品股份有限公司奈曼四区一场生猪养殖项目","通辽市","奈曼旗","西辽河","2017年","内蒙古奈曼牧原农牧有限公司","主要建设猪舍、粪污处理设施、沼液农灌设施、有机肥制造工程及供电、供热等辅助工程",34094.92]
[8,"牧原食品股份有限公司奈曼四区二场生猪养殖项目","通辽市","奈曼旗","西辽河","2017年","内蒙古奈曼牧原农牧有限公司","主要建设猪舍、粪污处理设施、沼液农灌设施、有机肥制造工程及供电、供热（依托四区一场项目）等辅助工程",3446.71]
[9,"赤峰凌志食品有限公司马铃薯全粉加工技改项目","赤峰市","翁牛特旗","少郎河","2016年-2017年","赤峰凌志食品有限公司","配套年处理废水12万吨污水处理设施",2680]
[10,"布尔台矿矿井水提标改造项目","鄂尔多斯市","伊金霍洛旗","乌兰木伦河","2016年-2017年","伊金霍洛镇人民政府","将7000m吨/日污水处理厂出水提标改造到地表Ⅲ类或矿井水全部回用",342.56]
[11,"乌兰木伦矿矿井水提标改造项目","鄂尔多斯市","伊金霍洛旗","乌兰木伦河","2016年-2017年","伊金霍洛镇人民政府","将10000吨/日污水处理厂出水提标改造到地表Ⅲ类或矿井水全部回用",636.39]
[12,"补连塔矿矿井水提标改造项目","鄂尔多斯市","伊金霍洛旗","乌兰木伦河","2016年-2017年","伊金霍洛镇人民政府","将10000吨/日污水处理厂出水提标改造到地表Ⅲ类或矿井水全部回用或矿井水全部回用",640]
[13,"上湾煤矿矿井水提标改造项目","鄂尔多斯市","伊金霍洛旗","乌兰木伦河","2016年-2017年","伊金霍洛镇人民政府","将7000吨/日污水处理厂提标改造到地表Ⅲ类",500]
[14,"赛蒙特尔矿矿井水提标改造项目","鄂尔多斯市","伊金霍洛旗","乌兰木伦河","2016年-2017年","伊金霍洛镇人民政府","将36000吨/日污水处理厂提标改造到地表Ⅲ类或矿井水全部回用",1300]
[15,"淖尔壕矿矿井水提标改造项目","鄂尔多斯市","伊金霍洛旗","乌兰木伦河","2016-2017年","伊金霍洛镇人民政府","将36000吨/日污水处理厂提标改造到地表Ⅲ类或矿井水全部回用",2500]
[16,"国华电厂循环冷却水废水深度处理","鄂尔多斯市","准格尔旗","龙王沟","2017年","准格尔旗人民政府","550吨/小时循环冷却水废水深度处理",6500]
[17,"巴彦淖尔市中河番茄食品有限公司污水处理系统提标技术改造项目","巴彦淖尔市","杭锦后旗","总排干","2017年","巴彦淖尔市中河番茄食品有限公司","新建日处理污水3600吨的“沉淀+好氧”工艺的污水处理站一座",450]
[18,"乌拉特后旗紫金矿业有限公司三贵口尾矿库增设环保截渗措施工程","巴彦淖尔市","乌拉特后旗","无","2017年","乌拉特后旗紫金矿业有限公司","本项目主要包括：截渗坝和防渗墙、截渗帷幕、降水井及抽排设施、消力池防渗和其它辅助设施，对尾矿库坝体渗水进行截留回收利用",2138.3]
[19,"泰盛兴业（内蒙古）食品有限公司8000m3/d番茄加工废水处理系统技改工程","巴彦淖尔市","乌拉特前旗","乌梁素海","2017年","泰盛兴业（内蒙古）食品有限公司","增加深化池，提高污水处理能力；更换新式曝气盘等",848]
[20,"巴彦淖尔市农垦蒙达肉联加工有限责任公司污水处理系统建设项目","巴彦淖尔市","乌拉特前旗","乌梁素海","2017年","巴彦淖尔市农垦蒙达肉联加工有限责任公司","建设污水收集管网及暂存罐，实现综合利用",20]
[21,"内蒙古蒙渊食品有限公司污水处理系统建设项目","巴彦淖尔市","乌拉特前旗","乌梁素海","2017年","内蒙古蒙渊食品有限公司","建设污水收集管网及暂存罐，实现综合利用",20]
[22,"乌海热电厂中水回用项目","乌海市","海勃湾区","黄河","2017年","环保局、水务局","对现有中水处理系统进行工艺优化改造，中水回用处理700吨/小时",1483]
[23,"华电乌达热电中水回用项目","乌海市","乌达区","黄河","2017年","环保局、水务局","完善中水回用系统，3*75吨/小时",3788]
[24,"君正发电厂中水回用项目","乌海市","乌达区","黄河","2017年","环保局、水务局","新建处理能力为293吨/小时的中水回用系统一套",5100]
[25,"内蒙古达康实业股份有限公司双氧水污水综合处理项目","阿拉善盟","阿拉善经济开发区","黄河","2015年-2017年","阿拉善经济开发区","各类机泵25台，压滤机1台，调节池、沉降池等共10座水池，监控设备等。",900]
[26,"中盐吉兰泰氯碱化工有限公司水、汽系统节能减排综合治理项目","阿拉善盟","阿拉善经济开发区","黄河","2016年-2017年","阿拉善经济开发区","对氯乙烯单体VCM转化余热和HCl合成余热回收利用改造，对烧碱厂蒸发工序二厂蒸汽冷凝水回用至电解槽技术改造，对纯水供应系统技术改造，对污水系统综合治理项目，含汞废水深度处理等方面改造工程。",2480]
[27,"内蒙古利元科技有限公司污水分质处理、中水回用项目","阿拉善盟","腾格里经济技术开发区","黄河","2016年-2017年","腾格里经济技术开发区","多效蒸发系统，膜处理系统，稀硫酸提浓处理系统",1189]
[28,"内蒙古津盟化工有限公司MVR处理污水项目","阿拉善盟","腾格里经济技术开发区","黄河","2016年-2017年","腾格里经济技术开发区","在原有的污水处理工艺基础上对工艺进行变更，主要建设内容包括MVR蒸发浓缩系统、生化处理系统及相关的设施构筑物的建设",2600]

{"sheet":"2-5农村环境综合","index":4,"n_rows":158,"n_cols":7,"rows_kept":158,"merged":[[0,0,0,6],[1,0,2,0],[1,1,2,1],[1,2,2,2],[1,3,2,3],[1,4,1,5],[1,6,2,6],[3,0,19,0],[3,1,19,1],[3,2,19,2],[3,3,4,3],[3,6,4,6],[5,3,6,3],[5,6,6,6],[9,3,11,3],[9,6,11,6],[12,3,14,3],[12,6,14,6],[15,3,16,3],[15,6,16,6],[17,3,18,3],[17,6,18,6],[20,0,28,0],[20,1,28,1],[20,2,28,2],[29,0,38,0],[29,1,38,1],[29,2,38,2],[29,3,32,3],[33,3,38,3],[39,0,63,0],[39,1,63,1],[39,2,63,2],[39,3,41,3],[42,3,46,3],[47,3,52,3],[53,3,58,3],[59,3,60,3],[61,3,63,3],[64,0,80,0],[64,1,80,1],[64,2,80,2],[64,3,66,3],[67,3,68,3],[69,3,71,3],[74,3,76,3],[77,3,78,3],[79,3,80,3],[81,0,118,0],[81,1,118,1],[81,2,118,2],[81,3,82,3],[83,3,85,3],[86,3,92,3],[96,3,100,3],[101,3,106,3],[107,3,110,3],[111,3,116,3],[117,3,118,3],[119,0,123,0],[119,1,123,1],[119,2,123,2],[124,0,138,0],[124,1,138,1],[124,2,138,2],[124,3,130,3],[131,3,138,3],[139,0,145,0],[139,1,145,1],[139,2,145,2],[146,0,152,0],[146,1,152,1],[146,2,152,2],[154,0,156,0],[154,1,156,1],[154,2,156,2],[157,0,157,1]],"flags":["formulas_cached_only"]}
["表5    农村环境综合整治项目表"]
["序号","盟市","自治区下达的年度任务数","旗县区","所在乡镇（街道）",null,"计划完成建制村数量\n（个）"]
[{"$nulls":4},"名称","行政区划代码"]
[1,"呼和浩特市",30,"赛罕区","金河镇","150105104000",4]
[{"$nulls":4},"黄合少镇","150105103000"]
[{"$nulls":3},"土默特左旗","察素齐镇","150121100000",3]
[{"$nulls":4},"毕克齐镇","150121101000"]
[{"$nulls":3},"新城区","保合少镇","150102100000",4]
[{"$nulls":3},"玉泉区","昭君办事处","150104100000",3]
[{"$nulls":3},"和林格尔县","盛乐经济园区","150123101000",3]
[{"$nulls":4},"舍必崖乡","150123203000"]
[{"$nulls":4},"城关镇","150123101000"]
[{"$nulls":3},"托克托县","五申镇","150122100000",3]
[{"$nulls":4},"伍什家镇","150122103000"]
[{"$nulls":4},"黄河湿地管委会","150122100000"]
[{"$nulls":3},"清水河县","城关镇","150124100000",3]
[{"$nulls":4},"宏河镇","150124101000"]
[{"$nulls":3},"武川县","哈乐镇","150125101000",3]
[{"$nulls":4},"耗赖山乡","150125214000"]
[{"$nulls":3},"回民区","攸攸板镇","150103100000",4]
[2,"包头市",20,"昆区","卜尔汉图镇",150203102000,5]
[{"$nulls":3},"青山区","青福镇",150204100000,2]
[{"$nulls":3},"九原区","阿嘎如泰苏木",150207202000,1]
[{"$nulls":3},"东河区","河东镇",150202100000,2]
[{"$nulls":3},"高新区","稀土路街道办事处",150204400000,4]
[{"$nulls":3},"石拐区","五当召镇",150205101000,1]
[{"$nulls":3},"固阳县","兴顺西镇",150222107000,1]
[{"$nulls":3},"土右旗","沟门镇",150221107000,3]
[{"$nulls":3},"达茂旗","查干哈达苏木",150223215000,1]
[3,"呼伦贝尔市",25,"新巴尔虎左旗","吉布胡郎图苏木",150726205000,3]
[{"$nulls":4},"阿木古郎镇",150726102000,5]
[{"$nulls":4},"罕达盖苏木",150726204000,2]
[{"$nulls":4},"甘珠尔苏木",150726206000,1]
[{"$nulls":3},"新巴尔虎右旗","阿拉坦额莫勒镇","150727100000",3]
[{"$nulls":4},"阿日哈沙特镇",150727101000,2]
[{"$nulls":4},"克尔伦苏木",150727201000,3]
[{"$nulls":4},"贝尔苏木",150727200000,2]
[{"$nulls":4},"达赉苏木",150727202000,2]
[{"$nulls":4},"宝格德乌拉苏木",150727203000,2]
[4,"兴安盟",30,"科右中旗","巴彦呼舒镇",152222100000,4]
[{"$nulls":4},"代钦塔拉苏木",152222200000,1]
[{"$nulls":4},"巴彦淖尔苏木",152222205000,1]
[{"$nulls":3},"乌兰浩特市","乌兰哈达镇 ",152201100000,1]
[{"$nulls":4},"太本站镇",152201102000,1]
[{"$nulls":4},"义勒力特镇 ",152201103000,1]
[{"$nulls":4},"斯力很现代农业园区",152201100000,1]
[{"$nulls":4},"葛根庙镇",152201101000,1]
[{"$nulls":3},"科右前旗","科尔沁镇",152221100000,1]
[{"$nulls":4},"察尔森镇",152221106000,1]
[{"$nulls":4},"巴拉格歹乡",152221203000,1]
[{"$nulls":4},"额尔格图镇",152221107000,1]
[{"$nulls":4},"大石寨镇",152221103000,1]
[{"$nulls":4},"德伯斯镇 ",152221102000,1]
[{"$nulls":3},"扎赉特旗","新木镇",152223000000,1]
[{"$nulls":4},"阿尔本格勒镇",152223004000,1]
[{"$nulls":4},"巴达尔胡镇",152223005000,1]
[{"$nulls":4},"胡尔勒镇",152223005000,1]
[{"$nulls":4},"努文牧仁乡",152223005000,1]
[{"$nulls":4},"好力宝乡",152223005000,1]
[{"$nulls":3},"阿尔山","白狼镇",152202001000,1]
[{"$nulls":4},"明水河镇",152202003000,1]
[{"$nulls":3},"突泉","杜尔基镇 ",152224000000,3]
[{"$nulls":4},"永安镇",152224000000,1]
[{"$nulls":4},"水泉镇",152224000000,1]
[5,"通辽市",39,"科尔沁区","木里图镇",150502103000,2]
[{"$nulls":4},"钱家店",150502101000,1]
[{"$nulls":4},"余粮堡",150502102000,1]
[{"$nulls":3},"开发区","河西街道",150502020000,1]
[{"$nulls":4},"辽河镇",150502030000,2]
[{"$nulls":3},"科左中旗","希伯花镇",150521107000,1]
[{"$nulls":4},"舍伯吐镇",150521102000,4]
[{"$nulls":4},"保康镇",150521100000,3]
[{"$nulls":3},"库伦旗","库伦镇",150524100000,10]
[{"$nulls":3},"科左后旗","甘旗卡",150522100000,2]
[{"$nulls":3},"奈曼旗","土城子",150525204000,1]
[{"$nulls":4},"青龙山",150525102000,1]
[{"$nulls":4},"义隆永",150525107000,5]
[{"$nulls":3},"扎鲁特旗","鲁北镇",150526100000,1]
[{"$nulls":4},"巨日合镇",150526103000,1]
[{"$nulls":3},"开鲁县","小街基镇",150523106000,2]
[{"$nulls":4},"麦新镇",150523103000,1]
[6,"赤峰市",47,"阿鲁科尔沁旗","天山镇",150421000000,1]
[{"$nulls":4},"双胜镇",150421002000,2]
[{"$nulls":3},"克什克腾旗","乌兰布统苏木",150425205000,1]
[{"$nulls":4},"巴彦查干苏木",150425203000,1]
[{"$nulls":4},"达日罕乌拉苏木",150425101000,1]
[{"$nulls":3},"宁城县","天义镇",150429100000,1]
[{"$nulls":4},"三座店镇",150429112000,1]
[{"$nulls":4},"存金沟乡",150429203000,1]
[{"$nulls":4},"黑里河镇",150429104000,1]
[{"$nulls":4},"八里罕镇",150429103000,1]
[{"$nulls":4},"汐子镇",150429107000,1]
[{"$nulls":4},"小城子镇",150429101000,1]
[{"$nulls":3},"元宝山区","平庄镇",150403103000,2]
[{"$nulls":3},"巴林左旗","林东镇",150422100000,4]
[{"$nulls":3},"巴林右旗","大板镇",150423100000,1]
[{"$nulls":3},"敖汉旗","下洼镇",150430105000,1]
[{"$nulls":4},"宝国吐乡",150430200000,1]
[{"$nulls":4},"古鲁板蒿乡",150430203000,1]
[{"$nulls":4},"四家子镇",150430101000,2]
[{"$nulls":4},"玛尼罕乡",150430105000,2]
[{"$nulls":3},"松山区","穆家营子镇",150404100000,1]
[{"$nulls":4},"当铺地满族乡",150404200000,1]
[{"$nulls":4},"夏家店乡",150404201000,1]
[{"$nulls":4},"安庆镇",150404107000,1]
[{"$nulls":4},"初头朗镇",150404101000,1]
[{"$nulls":4},"王府镇",150404103000,1]
[{"$nulls":3},"喀喇沁旗","西桥镇",150428106000,1]
[{"$nulls":4},"王爷府镇",150428102000,1]
[{"$nulls":4},"王爷府镇",150428102000,1]
[{"$nulls":4},"牛家营子镇",150428104000,1]
[{"$nulls":3},"翁牛特旗","乌丹镇",150426100000,2]
[{"$nulls":4},"桥头镇",150426103000,1]
[{"$nulls":4},"梧桐花镇",150426105000,1]
[{"$nulls":4},"亿合公镇",150426107000,1]
[{"$nulls":4},"广德公镇",150426104000,1]
[{"$nulls":4},"五分地镇",150426102000,1]
[{"$nulls":3},"林西县","新城子镇",150424101000,1]
[{"$nulls":4},"官地镇",150424104000,2]
[7,"锡林郭勒盟",20,"阿巴嘎旗","别力古台镇",152522100000,6]
[{"$nulls":3},"太仆寺旗","永丰镇",152527104000,2]
[{"$nulls":3},"正镶白旗","星耀镇",152529101000,10]
[{"$nulls":3},"正蓝旗","那日图苏木",152530201000,1]
[{"$nulls":3},"多伦县","西干沟乡",152531202000,1]
[8,"乌兰察布市",40,"兴和县","城关镇","150924106000",3]
[{"$nulls":4},"张皋镇","150924107000",1]
[{"$nulls":4},"鄂尔栋镇","150924109000",12]
[{"$nulls":4},"店子镇","150924110000",5]
[{"$nulls":4},"大库联乡","150924209000",1]
[{"$nulls":4},"民族团结乡","150924210000",1]
[{"$nulls":4},"大同夭乡","150924211000",5]
[{"$nulls":3},"丰镇市","黑土台镇","150981108000",1]
[{"$nulls":4},"隆盛庄镇","150981107000",3]
[{"$nulls":4},"巨宝庄镇","150981110000",3]
[{"$nulls":4},"红砂坝镇","150981109000",1]
[{"$nulls":4},"三义泉镇","150981111000",1]
[{"$nulls":4},"浑源窑乡","150981207000",1]
[{"$nulls":4},"官屯堡乡","150981209000",1]
[{"$nulls":4},"元山子乡","150981208000",1]
[9,"鄂尔多斯市",60,"东胜区","泊江海镇、铜川镇、罕台镇","150602000000",4]
[{"$nulls":3},"准格尔旗","薛家湾镇、沙圪堵镇、大路镇、龙口镇、准格尔召镇、十二连城乡、布尔陶亥苏木","150622000000",7]
[{"$nulls":3},"伊金霍洛旗","乌兰木伦镇、伊金霍洛镇、设札萨克镇、纳林陶亥镇、红庆河镇、苏布尔嘎镇","150627000000",16]
[{"$nulls":3},"乌审旗","嘎鲁图镇、无定河镇、乌审召镇、图克镇、乌兰陶勒盖镇、苏力德苏木","150626000000",9]
[{"$nulls":3},"杭锦旗","巴拉贡、呼和木独镇、吉日嘎郎图镇、独贵塔拉镇","150625000000",6]
[{"$nulls":3},"鄂托克旗","乌兰镇、蒙西镇、棋盘井镇、木凯淖尔镇、苏米图苏木、阿尔巴斯苏木","150624000000",11]
[{"$nulls":3},"鄂托克前旗","敖镇、上海庙镇、昂素镇、城川镇","150623000000",7]
[10,"巴彦淖尔市",109,"临河区","狼山镇、新华镇、干召庙镇、乌兰图克镇、双河镇、城关镇、白脑包镇、八一乡、曙光乡",150802000000,32]
[{"$nulls":3},"磴口县","隆盛合镇、巴彦高勒镇、沙金苏木",150822000000,5]
[{"$nulls":3},"五原县","隆兴昌镇、新公中镇、复兴镇、套海镇、银锭图镇、胜丰镇、天吉泰镇、和胜乡（建丰农场）、塔尔湖镇、丰裕办事所",150821000000,35]
[{"$nulls":3},"杭锦后旗","双庙镇、蛮会镇、头道桥镇、三道桥镇、蒙海镇",150826000000,5]
[{"$nulls":3},"乌拉特前旗","乌拉山镇、新安镇、西小召、苏独仑镇、大佘太镇、明安镇",150823000000,24]
[{"$nulls":3},"乌拉特中旗","石哈河镇、德岭山镇、海流图镇、乌加河镇、甘其毛都镇",150824000000,7]
[{"$nulls":3},"乌拉特后旗","巴音宝力格镇",150825000000,1]
[11,"乌海市",2,"海南区","巴音陶亥镇",150303104000,2]
[12,"阿拉善盟",9,"阿左旗","巴彦浩特镇、嘉尔嘎勒赛汉镇",152921000000,6]
[{"$nulls":3},"阿右旗","雅布赖镇",152922000000,1]
[{"$nulls":3},"额济纳旗","东风镇、赛汉陶来苏木",152923000000,2]
["合计",null,431,{"$nulls":3},431]

{"sheet":"2-6水源地规范化建设","index":5,"n_rows":32,"n_cols":11,"rows_kept":32,"merged":[[0,0,0,10]],"flags":["formulas_cached_only"]}
["表6  水源地规范化建设项目表"]
["序号","水源地名称","水源代码","水源类型","服务人口（万人）","所在流域","盟市","旗县区","项目内容","投资\n（万元）","完成时限"]
[1,"呼和浩特市城区地下水饮用水水源地","DA8100150101000G0001","地下水型",95.71,"黄河流域","呼和浩特市","新城区","新城区水源井围封",60.8,"2017年"]
[2,"鄂伦春自治旗大杨树镇水源地保护工程","AD1400150723101G03","地下水型",3,"甘河支流","呼伦贝尔市","鄂伦春旗","一级保护区：隔离防护采用水泥桩、刺铁线型式，警示牌11个，界桩111个；二级保护区：警示牌14个，界桩142个；准保护区：警示牌14个，界桩145个。植树绿化231.7万棵，总种植面积8910亩；清运垃圾总计3218吨；回填土方22000m³",null,"2017年\n"]
[3,"乌兰浩特市新建一水源地保护工程","AD280115220100G001","地下水",4.1,"松花江","兴安盟","乌兰浩特市","（1）一级保护区隔离防护工程，建高1.5米，5×5厘米网眼的钢丝围栏6554延长米，警示宣传牌8块，界标16块，宣传牌16块。（2）一级保护区清拆工程，拆迁与取水工程设施无关的建筑，搬迁居民4户，餐饮服务业2个，养殖企业1个，加工企业1个。（3）生态修复与建设工程，一水源一级保护生态全面恢复，种植草皮和水源涵养林78公顷。（4）非点源污染整治工程，征用一级保护区草地、耕地、居民点、道路等共875亩，消除农业生产中使用的化肥、农药等和居民生活对水源地水质的不利影响",16395.1,"2016年—2017年"]
[4,"乌兰浩特市二水源地扩建部分保护工程","AD280115220100G002"," 地下水",20.5,"松花江","兴安盟","乌兰浩特市","（1）一级保护区隔离防护工程，建高1.5米，5×5厘米网眼的钢丝围栏12200延长米，警示宣传牌4块，界标8块，宣传牌8块。（2）一级保护区清拆工程，搬迁居民240户。（2）生态修复与建设工程，二水源扩建部分一级保护区生态全面恢复，种植草皮和水源涵养林308公顷。（4）非点源污染整治工程，征用一级保护区居民点713亩，消除居民点生产中的产生的污水等对水源地水质的不利影响",18029.66,"2016年5月—2018年10月"]
[5,"阿荣旗那吉镇新区饮用水源地保护工程","-","地下水型","-","阿伦河新发断面","呼伦贝尔市","阿荣旗","保护区划界面积123万平方米，边界总长10.8公里，建水源涵养林24.32万棵，截污管道6406米，污水截留明渠1548米，村庄新建绿地25000平方米，建隔离栏10800米，设立界标236个，警示标牌24个，建监测水源井3眼及垃圾收集和转运设施",null,"2017年"]
[6,"通辽市科尔沁区集中式饮用水水源地","BA0300150502000G0001","地下水",44.4485,"辽河流域","通辽市","科尔沁区","建设电子围栏",75,"2017年底"]
[7,"通辽经济技术开发区集中式饮用水水源地","BA0300150502000G0002","地下水",8.8825,"辽河流域","通辽市","通辽经济技术开发区","建设电子围栏",75,"2017年底"]
[8,"松山区夏家店乡地下水型水源地","BA0103150404201G01","地下水型",0.1816,"辽河流域","赤峰市","松山区","关闭排污口",104,"2017年"]
[9,"松山区初头朗镇地下水型水源地","BA0100150404101G01","地下水型",0.8,"辽河流域","赤峰市","松山区","关闭排污口",60,"2017年"]
[10,"集宁区霸王河水源地","MG1600150902000G0003","地下水",6.3,"西北诸河","乌兰察布市","集宁区","对一级保护区进行物理隔离防护、违规建筑清拆工程和在线监控工程，总物理防护16000米，总清拆面积8610平方米，在线监控1套",2480,"2018年"]
[11,"集宁区白家湾-幸福村水源地","MG1600150902000G0006","地下水",11,"西北诸河","乌兰察布市","集宁区","对一级保护区进行物理隔离防护和在线监控工程，总物理防护13600米，在线监控1套",347,"2019年"]
[12,"集宁区赞达营-梁家村水源地","MG1600150902000G0008","地下水",6.07,"西北诸河","乌兰察布市","集宁区","对一级保护区进行物理隔离防护和在线监控工程，总物理防护6400米，在线监控1套",248,"2019年"]
[13,"临河区黄河水厂水源地","—","地表水",16.8,"黄河流域","巴彦淖尔市","临河区","2个取水口安装视频监控",5,"2017年"]
[14,"磴口县巴彦高勒镇新水源地城镇水源地","DA6301150822100G01","地下水",5.5,"黄河流域","巴头彦淖市","磴口县","隔离防护、标志牌设置、生态修复及建设等综合保护措施。",280,"2017年"]
[15,"五原县新公中镇饮用水水源地","DA7000150821103G01","地下水",1.1372,"黄河流域上游干流区间","巴彦淖尔市","五原县","标识牌、网围栏",55,"2017年"]
[16,"五原县天吉泰镇饮用水水源地","DA7000150821104G01","地下水",0.9339,"黄河流域上游干流区间","巴彦淖尔市","五原县","标识牌、网围栏",55,"2017年"]
[17,"五原县银定图镇饮用水水源地","DA7000150821105G01","地下水",2.2827,"黄河流域上游干流区间","巴彦淖尔市","五原县","标识牌、网围栏",55,"2017年"]
[18,"五原县东部五乡镇和什巴圪图农村安全饮用水水源地","—","地下水",5.7771,"黄河流域上游干流区间","巴彦淖尔市","五原县","2017年完成征地、清理耕地",1240,"2017年"]
[19,"乌拉山镇饮用水源地","DA7000150823100G0001","承压水",12,"黄河流域","巴彦淖尔市","乌拉特前旗","保护区围封、监控设施安装、标志碑、警示牌设立、防洪坝等",174.87,"2017年"]
[20,"小佘太镇饮用水源地","DA7000150823107G01","潜水",0.1,"黄河流域","巴彦淖尔市","乌拉特前旗","保护区围封、监控设施安装、标志碑、警示牌设立、防洪坝等",39.7,"2017年"]
[21,"海南区水源地规范化建设","DA0000150303000G05","地下水",6,"黄河流域","乌海市","海南区","隔离防护、标志牌设置",28,"2017年"]
[22,"海勃湾区千里山镇千钢社区水源地规范化建设","DA0000150302101G01","地下水",0.31,"黄河流域","乌海市","海勃湾区","隔离防护、标志牌设置",null,"2017-2019年"]
[23,"海勃湾区千里山镇团结新村水源地规范化建设","DA0000150302101G02","地下水",0.27,"黄河流域","乌海市","海勃湾区","隔离防护、标志牌设置",null,"2017-2019年"]
[24,"乌达区乌兰卓尔镇泽园新村水源地规范化建设","DA0000150304101G08","地下水",0.158,"黄河流域","乌海市","乌达区","隔离防护、标志牌设置",null,"2017-2019年"]
[25,"海南区拉僧庙镇水源地规范化建设","DA0000150303103G04","地下水",0.8,"黄河流域","乌海市","海南区","隔离防护、标志牌设置",null,"2017-2019年"]
[26,"海南区公乌素镇水源地规范化建设","DA0000150303103G05","地下水",1.1,"黄河流域","乌海市","海南区","隔离防护、标志牌设置",null,"2017-2019年"]
[27,"海南区巴音陶亥镇雀儿沟水源地规范化建设","DA0000150303103G06","地下水",0.9,"黄河流域","乌海市","海南区","隔离防护、标志牌设置",null,"2017-2019年"]
[28,"海勃湾北水源地","DA0000150302000G0002","地下水",23.65,"黄河流域","乌海市","海勃湾区","新建海勃湾区北部净水厂配水井、综合水池、膜车间及附属设备间、清水池、吸水井、送水泵房、加氯间、水质监测中心等，10万吨/日",39000,"2017-2018年"]
[29,"乌达城区水源地","DA0000150304000G0001","地下水",5.7,"黄河流域","乌海市","乌达区","新建乌达区净水厂3.5万吨/日",4499.32,"2017-2018年"]
[30,"海南区西水源地","DA0000150303000G0002","地下水",2.6,"黄河流域","乌海市","海南区","新建海南区净水厂，主要建筑物包括：配水井、原水池、浓水池、超滤产水池、产品水池、反冲洗排水池、膜车间及附属设备间、2座清水池、吸水井、综合楼、仓库及机修车间、堆棚、燃气锅炉房、门卫室等，2万吨/日",15022,"2017-2018年"]

{"sheet":"附表2-8其他类项目","index":6,"n_rows":27,"n_cols":9,"rows_kept":27,"merged":[[0,0,0,8],[1,0,2,0],[1,1,2,1],[1,2,1,3],[1,4,2,4],[1,5,2,5],[1,6,2,6],[1,7,2,7],[1,8,2,8]],"flags":["formulas_cached_only"]}
["表7  其他类项目"]
["序号","项目名称","建设地点",null,"目标水体","建设周期","责任单位","建设内容及规模","项目总投资（万元）"]
[null,null,"地级行政区","县级行政区"]
[1,"高盐水减量化治理工程\n","呼和浩特市","托克托县","大黑河","2017年","托克托工业园区管委会 、托克托县环保局\n","引进环境污染第三方治理公司，处理高盐水晾晒池积存高盐水。\n",3000]
[2,"呼伦湖湖区水环境质量及水生物环境质量调查方案","呼伦贝尔市","满洲里市、新右旗、新左旗、扎赉诺尔区","呼伦湖-小河口、甘珠花断面","2016年-2018年","呼伦贝尔市环境科学研究所","系统摸清湖区水质及水生态情况，调查湖区主要污染物分布情况。",284.4]
[3,"呼伦湖流域水质监测系统建设项目","呼伦贝尔市","满洲里市、新右旗、新左旗、扎赉诺尔区","呼伦湖-小河口、甘珠花断面","2016年-2018年","呼伦贝尔市环境监测中心站","建水质自动站7个，采购仪器设备112台/套。",3920]
[4,"多伦县新沃源生物有机肥业有限公司年产2万吨微生物有机肥建设项目","锡林郭勒盟","多伦县","滦河","2015年-2017年","多伦县新沃源生物有机肥业有限公司","建设年产2万吨微生物有机肥",400]
[5,"乌兰察布市环境监测中心站水环境能力建设项目","乌兰察布市","乌兰察布市","海河、黄河流域控制断面、岱海流域","2016年-2018年","乌兰察布市环境监测站","购置水环境监测仪器设备",650]
[6,"乌兰察布市环境水环境监管能力建设项目","乌兰察布市","乌兰察布市","海河、黄河流域控制断面、岱海流域","2016年-2018年","乌兰察布市环境保护局","购置水环境监察执法及应急监测仪器设备",704.16]
[7,"乌兰察布市废水处理技术研发中心建设项目","乌兰察布市","乌兰察布市","海河、黄河流域控制断面、岱海流域","2016年-2018年","内蒙古山羽环保科技发展有限公司","实验室建筑面积1500m2、可研办公楼1000m2、宿舍、食堂、配电室等附属配套设施1000m2。",4000]
[8,"岱海及乌兰察布市水生态安全调查与评估","乌兰察布市","乌兰察布市","海河、黄河流域控制断面、岱海流域","2016年-2016年","乌兰察布市环境保护局","对岱海、黄旗海、海河、黄河流域及饮用水源地水生态安全调查与评估",600]
[9,"乌兰察布市岱海流域水质自动监测站建设项目","乌兰察布市","凉城县","岱海湖泊","2016年-2017年","凉城县环保局 ","建设三套水质自动监测站，点位分别为岱海电厂入湖口、弓坝河入湖口、三道河入湖口",690]
[10,"凉城县弓坝河生物净化工程工程","乌兰察布市","凉城县弓坝河水库","岱海湖泊","2016年-2018年","凉城县环保局、水利局","修建水坝5座，建人工湿地强化处理系统2万m3.",3676]
[11,"凉城县岱海湖滨缓冲带修复和重建工程","乌兰察布市","凉城县岱海西岸","岱海湖泊","2016年-2016年","凉城县环保局","在湖区东南西三处生态修复1000亩湿地，湖底、渠道清淤疏浚3200m³。",3500]
[12,"岱海电厂一期湿冷机组改造工程","乌兰察布市","凉城县","岱海湖泊","2017年-2019年","凉城县经信商务局","岱海电厂一期亚临界湿冷机组改造为临界空冷机组",119000]
[13,"规模化畜禽养殖场配套污染防治设施建设","鄂尔多斯市","除康巴什新区外的各旗区","黄河流域","2017年","除康巴什新区外各旗区人民政府","57家规模化畜禽养殖场配套建设粪便污水贮存、处理、利用设施 ",2200]
[14,"内蒙古蒙达发电有限责任公司入黄河排水口移位工程","鄂尔多斯市","达拉特旗","黄河流域","2017年","达拉特旗人民政府","将现排黄口由西向东移至第二座黄河大桥下游",70]
[15,"鄂尔多斯市高效节水增效项目","鄂尔多斯市","除东胜区、康巴什新区外的各旗区","黄河流域","2017年","各旗区人民政府","新增滴灌面积25.38万亩",25000]
[16,"碱柜中型灌区（二期）节水配套改造项目","鄂尔多斯市","鄂托克旗","黄河流域","2016-2017年","鄂托克旗人民政府","泵站改造1座、渠道衬砌5.24km",1448.15]
[17,"黄河内蒙古乌梁素海综合治理项目水土保持专项项目","巴彦淖尔市","乌拉特前旗","乌梁素海","2015-2020年","乌梁素海管委会","营造水土保持乔木林、灌木林，作业路，标志牌等。",33056]
[18,"黄河巴彦淖尔段入境-三盛公水质自动监测站能力建设","巴彦淖尔市","磴口县","乌梁素海","2016年-2017年","巴彦淖尔市环境保护监测站","在黄河巴彦淖尔段入境三盛公建设一水质自动监测站，包括站房和仪器设备的建设。拟监测项目包括常规五参数（水温、pH值、电导率、溶解氧、浊度）、CODmn、氨氮、总有机碳、流量",350]
[19,"黄河巴彦淖尔段出境-水质自动监测站能力建设","巴彦淖尔市","乌拉特前旗","乌梁素海","2017年-2018年","巴彦淖尔市环境保护监测站","在黄河巴彦淖尔段出境建设一水质自动监测站，包括站房和仪器设备的建设。拟监测项目包括常规五参数（水温、pH值、电导率、溶解氧、浊度）、CODmn、氨氮、总有机碳、流量、氯化物",400]
[20,"乌梁素海流域水质在线自动监测能力建设项目","巴彦淖尔市","乌拉特前旗、磴口县、五原县、杭锦后旗、临河区","乌梁素海","2017年-2020年","巴彦淖尔市信息中心","对乌梁素海流域新建10个水质自动监测站的监测设备购买及安装调试。",1140]
[21,"乌梁素海环境信息化建设项目","巴彦淖尔市","乌拉特前旗、临河区","乌梁素海","2017年-2020年","巴彦淖尔市信息中心","以巴彦淖尔市第二污水处理厂及联邦制药污水处理厂为试点建设安装污水处理行为分析系统，建立污水治理设施运行的监控分析模型，为乌梁素海水质分析提供可靠的数据来源。",110]
[22,"水污染防治监测能力建设","巴彦淖尔市","临河区","黄河","2017年-2019年","巴彦淖尔市环境保护监测站","电感耦合等离子体发射光谱—质谱仪、离子色谱仪、气相色谱仪、吹扫捕集自动进样器、气相色谱质谱联用仪、液相色谱仪、冷原子吸收测汞仪、分光光度计、天平等，共计60台/套仪器设备",783]
[23,"海勃湾4万吨净水厂","乌海市","海勃湾区","黄河","2017年","城投公司","稳定运行",4844]
[24,"乌达区水源井保护工程","乌海市","乌达区","黄河","2017-2018年","环保局","水源井共计13眼防护围栏",100]